## Agile Sprint Backlog
AGILE SPRINT BACKLOG WITH BURNDOWN CHART
BACKLOG TASK & ID | STORY POINTS | ASSIGNED TO | STATUS | ORIGINAL ESTIMATE | DAY 1 | DAY 2 | DAY 3 | DAY 4 | DAY 5 | DAY 6 | SPRINT REVIEW
[5 empty] | Tursday | Thursday | Tuesday | Thursday | Tuesday | Thursday
User Story #1 | 8
Task |  |  |  | 7 | 5 | 3 | 0 | 0 | 10 | 0 | 0
Task |  |  |  | 3 | 1 | 1 | 5 | 0 | 5 | 1 | 0
Task |  |  |  | 1 | 0.5 | 0 | 3 | 0 | 6 | 0 | 0
Task |  |  |  | 0.5 | 1 | 2 | 3 | 1 | 4 | 0 | 0
User Story #2 | 1
Task |  |  |  | 3 | 3 | 0.5 | 0.5 | 0 |  | 0 | 2
Task |  |  |  | 3 | 5 | 5 | 1 | 1 |  | 1 | 0
Task |  |  |  | 2 | 2 | 5 | 0 | 1 |  | 0 | 1
Task |  |  |  | 5 | 5 | 9 | 5 | 1 |  | 0 | 1
User Story #3 | 5
Task |  |  |  | 8 | 6 | 0 | 0 | 0 |  | 0 | 0
Task |  |  |  | 3 | 1 | 3 | 3 | 3 |  | 0 | 0
Task |  |  |  | 1.5 | 1 | 0.5 | 0.5 | 1 |  | 1 | 0
Task |  |  |  | 2 | 0.5 | 0 | 0 | 0 |  | 0 | 3
User Story #4 | 8
Task |  |  |  | 9 | 4 | 2 | 2 | 1 |  | 1 | 0
Task |  |  |  | 6 | 6 | 3 | 3 | 3 |  | 1 | 1
Task |  |  |  | 6 | 2 | 8 | 8 | 1 |  | 0 | 1
Task |  |  |  | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  | 0 | 0
User Story #5 | 3
Task |  |  |  | 2 | 1 | 1 | 1 | 0.5 |  | 1 | 1
Task |  |  |  | 6 | 6 | 6 | 0.5 | 3 |  | 9 | 0
Task |  |  |  | 9 | 9 | 9 | 4 | 3 |  | 3 | 3
Task |  |  |  | 0.5 | 0.5 | 0.5 | 1 | 0.5 |  | 0 | 1
TOTAL |  |  |  | 78 | 60 | 59 | 41 | 20 | 25 | 18 | 14

## Agile Sprint Backlog - Sprint2
AGILE SPRINT BACKLOG TEMPLATE WITH BURNDOWN CHART
BACKLOG TASK & ID | STORY POINTS | ASSIGNED TO | STATUS | ORIGINAL ESTIMATE | DAY 1 | DAY 2 | DAY 3 | DAY 4 | DAY 5 | SPRINT REVIEW
User Story #1
Create Strategies |  | Orlando |  | 2 | 0.5 | 0.2 | 0.2 | 0 | 1 | 0.2
Create Wizard/Warrior with strat |  | Orlando |  | 1 | 0 | 0 | 0 | 0 | 1 | 0.3
Document |  | Orlando |  | 5 | 0 | 0.3 | 0.3 | 1 | 0.5 | 0.5
Writing tests |  | Orlando |  | 13 | 0 | 0 | 0 | 2 | 1 | 0
User Story #2
Create Strategies |  | Owen |  | 2 | 0 | 0 | 1 | 0.5 | 0.5 | 0.2
Create Warrior/Wizard with strategy |  | Owen |  | 1 | 0 | 0 | 0 | 0 | 1 | 0.5
UML Diagram |  | Owen |  | 2 | 1 | 0 | 0 | 0 | 1 | 0.1
Writing Tests |  | Owen |  | 5 | 0 | 0 | 2.5 | 1 | 1.5 | 0.2
USer Story #3
Create Strategies |  | Seth |  | 3 | 1 | 0.5 | 0.75 | 0.25 | 1 | 0.5
Create People with strats |  | Seth |  | 2 | 0 | 0 | 0 | 1 | 1 | 0.5
Document |  | Seth |  | 2 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.75
Testing |  | Seth |  | 5 | 1 | 0.5 | 0.5 | 1 | 2 | 0.5
User Story #4
Task
Task
Task
Task
User Story #5
Task
Task
Task
Task
TOTAL |  |  |  | 43 | 3.75 | 1.75 | 5.5 | 7 | 11.75 | 4.25

## Copy of Agile Sprint Backlog -
AGILE SPRINT BACKLOG TEMPLATE WITH BURNDOWN CHART
BACKLOG TASK & ID | STORY POINTS | ASSIGNED TO | STATUS | ORIGINAL ESTIMATE | DAY 1 | DAY 2 | DAY 3 | DAY 4 | DAY 5 | SPRINT REVIEW
User Story #1
Update Documentation |  | Seth, Owen, Orlando | Not done | 2 | 0 | 1 | 0 | 1 | 1
Implemement Strategies into game |  | Seth, Owen, Orlando | Not done | 4 | 1 | 1 | 2 | 1 | 0
Update UML |  | Seth, Owen, Orlando | Not done | 2 | 1 | 0 | 0 | 0 | 1
User Story #2
User Story #3
User Story #4
Task
Task
Task
Task
User Story #5
Task
Task
Task
Task
TOTAL |  |  |  | 8 | 2 | 2 | 2 | 2 | 2 | 0

## Copy of Agile Sprint - Sprint4
AGILE SPRINT BACKLOG WITH BURNDOWN CHART
BACKLOG TASK & ID | STORY POINTS | ASSIGNED TO | STATUS | ORIGINAL ESTIMATE | DAY 1 | DAY 2 | DAY 3 | DAY 4 | DAY 5 | DAY 6 | SPRINT REVIEW
[5 empty] | Tursday | Thursday | Tuesday | Thursday | Tuesday | Thursday
User Story #1
100 Life point Limit |  | Owen | Complete | 2 | 1 | 0 | 0 | 0 | 0 | 0
Healer |  | Orlando | Complete | 4 | 0.3 | 0.2 | 0 | 0 | 0 | 0
Dice Class |  | Seth | Complete | 2 | 0 | 1 | 0 | 2 | 0 | 0
Distance |  | Owen | Complete | 3 | 0 | 1 | 0 | 0 | 0 | 0
Tribe of npc and traps (Artifacts) |  | Everyone | Complete | 5 | 0 | 0 | 0 | 1 | 2 | 2
Multiple Strats (For respective classes) |  | Seth | Complete | 3 | 0 | 0.5 | 1 | 0 | 0 | 1
Multiple Strats (For respective classes) |  | Orlando | Complete | 4 | 0 | 0 | 1 | 1 | 0 | 0
Multiple Strats (For respective classes) |  | Owen | Complete | 2 | 0 | 0 | 0 | 0 | 2 | 0
Random Seed |  | Seth | Complete | 1 | 1 | 0 | 0 | 0 | 0 | 0
Fix your strat (very weird)(Seth's strat is very very weird) |  | Seth | Complete | 1 | 0 | 0 | 1 | 0 | 0 | 0
GUI (low priority) |  |  |  | 6 | 0 | 0 | 0 | 0 | 0 | 0
User Story #2
Task
Task
Task
Task
User Story #3
Task
Task
Task
Task
User Story #4
Task
Task
Task
Task
User Story #5
Task
Task
Task
Task
TOTAL |  |  |  | 33 | 2.3 | 2.7 | 3 | 4 | 4 | 3 | 0